## Plan 1.0
PROJECT DEVELOPMENT PLAN
Project Name: ALIST Marketing - Facebook and LinkedIn Free Post
Creator : Shibu Kumar
Module |  | Start Date | End Date | Status | Reviewed | Reviewed
Milestone 1
Week #1
Authentication (Facebook) | Assigned | Estimated Hours | Actual Hours | Developer | Project Manager | ALIST
Manage Personal Page authentication |  | 5
Manage Business Page authentication |  | 4
Manage reauthorization in case of Password change |  | 4
HTML Integration |  | 4
Manage Multiple Facebook Accounts |  | 8
Message Posting(Facebook)
Post message on Personal Page |  | 9
Post message on Business Page |  | 9
Add Photo with the Post |  | 2
| Total Hours | 45
Week #2
Message Posting(Facebook) | Assigned | Estimated Hours | Actual Hours | Developer | Project Manager | ALIST
Add Photo with the Post |  | 4
Schedule Post for future |  | 8
Cron job for posting message in future |  | 20
Sharing Privacy Setting (Personal Page) |  | 8
HTML Integration |  | 5
| Total Hours | 45
Milestone 2
Week #3
Message Posting(Facebook) | Assigned | Estimated Hours | Actual Hours | Developer | Project Manager | ALIST
Post message to multiple profiles |  | 10
Listing(Facebook)
Past Messages |  | 4
Future Messages |  | 4
Delete Post |  | 5
Republish post |  | 8
Draft your post |  | 4
HTML Integration |  | 4
URL Shortner
Url Shortner API Authentication |  | 6
| Total Hours | 45
Week #4
URL Shortner | Assigned | Estimated Hours | Actual Hours | Developer | Project Manager | ALIST
Convert Normal Url to Shortened Url |  | 12
API Implementation |  | 6
Reports of Shortened URL |  | 16
HTML Integration |  | 6
LinkedIn Post Sharing
Generating Access Token(Connect Account) |  | 5
| Total Hours | 45
Week #5
LinkedIn Post Listing | Assigned | Estimated Hours | Actual Hours | Developer | Project Manager | ALIST
Generate New Access token using refresh token in case access token gets expire |  | 6
Create and share post with LinkedIn users. |  | 6
Attach Image with the post |  | 4
Privacy settings(share with anyone, connections only) |  | 4
Schedule post for future |  | 9
LinkedIn Post Listing
Edit and Republish Post |  | 7
Draft your post |  | 5
Delete Post |  | 4
| Total Hours | 45
Week #6
LinkedIn Post Listing | Assigned | Estimated Hours | Actual Hours | Developer | Project Manager | ALIST
Past Messages |  | 5
Future Messages |  | 6
HTML Integration |  | 6
Twitter Status Update
Generate New Access token using refresh token in case access token gets expire |  | 6
Create and post Status on Twitter. |  | 4
Attach Image with the post |  | 3
Location Targeting |  | 4
Schedule post for future |  | 6
Twitter Post Listing
Edit and Republish Post |  | 5
| Total Hours | 45
Week #7
Twitter Post Listing | Assigned | Estimated Hours | Actual Hours | Developer | Project Manager | ALIST
Delete Post |  | 3
Draft your post |  | 3
Past Messages |  | 2
Future Messages |  | 2
HTML Integration |  | 6
Pinning a post on Pinterest
Authentication for generating Access Token |  | 8
Generate New Access token using refresh token in case access token gets expire |  | 8
Manage and save Access token in our database for accessing user profile |  | 6
API Implementation for fetching list of Boards on Pinterest |  | 7
| Total Hours | 45
Week #8
Pinning a post on Pinterest | Assigned | Estimated Hours | Actual Hours | Developer | Project Manager | ALIST
API implementation for creating new Board |  | 6
Pinning a post on any Board in Pinterest (API implementation) |  | 10
Attach image with the post |  | 5
Schedule post for future |  | 12
Pinterest Post Listing
Edit and Republish Post |  | 7
Delete Post(Also deletes from Pinterest) |  | 5
| Total Hours | 45
Week #9
Pinterest Post Listing | Assigned | Estimated Hours | Actual Hours | Developer | Project Manager | ALIST
Draft your post |  | 3
Show past messages sent |  | 3
Show future messages to be send |  | 3
HTML Integration |  | 6
Testing & Bug Fixing |  | 24
EventBrite Reporting
Authentication and generate access token |  | 6
| Total Hours | 45
Week #10
EventBrite Reporting | Assigned | Estimated Hours | Actual Hours | Developer | Project Manager | ALIST
Save access token |  | 8
Regenerate access token in case of expiration |  | 8
API Implementation for fetching Authenticated Users Events and saving into our database |  | 12
API Implementation for fetching Organizers details from ID |  | 8
API Implementation for fetching Venue details for each events |  | 9
| Total Hours | 45
Week #11
EventBrite Reporting | Assigned | Estimated Hours | Actual Hours | Developer | Project Manager | ALIST
API Implementation for fetching Category and SubCategory for each events |  | 8
Sales by Ticket Type |  | 16
Recent Orders Listing |  | 16
Attendee Summary |  | 5
| Total Hours | 45
Week #12
EventBrite Reporting | Assigned | Estimated Hours | Actual Hours | Developer | Project Manager | ALIST
Attendee Summary |  | 7
Summary of Sales |  | 16
Cron function for fetching Newly created event |  | 9
Cron function for fetching Order Details |  | 8
Cron function for fetching Attendees |  | 5
| Total Hours | 45
Week #13
EventBrite Reporting | Assigned | Estimated Hours | Actual Hours | Developer | Project Manager | ALIST
Cron function for fetching Attendees |  | 3
Cron function for fetching Sales data |  | 8
HTML Integration |  | 8
| Total Hours | 19
[7 empty] | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04 | Milestone : 8 | 2015-02-22 | 2015-03-04